## Timeline
Start Date | Hours of per week | Estimated Date of Completion
Enter the date you started studying | Enter the number you will commit | Lower Bound | Upper Bound
2021-01-25 | 10 | 2025-09-22 16:48 | 2026-09-20 07:12

## Curriculum Data
Courses | Topic | Duration | Effort | Total Hours Lower Bound | Start Date | End Date Estimate Lower Bound | Total Hours Upper Bound | Start Date | End Date Estimate Upper Bound | Actual End Date | Status | Prerequisites
Python for Everybody | Intro | 10 weeks | 10 hours/week | 100 | 2021-01-25 | 2021-04-05 | 100 | 2021-01-25 | 2021-04-05 |  | Lesson 2 Vid 3
Introduction to Computer Science and Programming using Python | Intro | 9 weeks | 15 hours/week | 135 | 2021-04-05 | 2021-07-08 12:00 | 135 | 2021-04-05 | 2021-07-08 12:00 |  |  | high school algebra
How to Code - Simple Data | Core Programming | 7 weeks | 8-10 hours/week | 56 | 2021-07-08 12:00 | 2021-08-16 16:48 | 70 | 2021-07-08 12:00 | 2021-08-26 12:00 |  |  | -
How to Code - Complex Data | Core Programming | 6 weeks | 8-10 hours/week | 48 | 2021-08-16 16:48 | 2021-09-19 07:12 | 60 | 2021-08-26 12:00 | 2021-10-07 12:00 |  |  | How to Code: Simple Data
Programming Languages, Part A | Core Programming | 5 weeks | 4-8 hours/week | 20 | 2021-09-19 07:12 | 2021-10-03 07:12 | 40 | 2021-10-07 12:00 | 2021-11-04 12:00 |  |  | How to Code (Hear instructor)
Programming Languages, Part B | Core Programming | 3 weeks | 4-8 hours/week | 12 | 2021-10-03 07:12 | 2021-10-11 16:48 | 24 | 2021-11-04 12:00 | 2021-11-21 07:12 |  |  | Programming Languages, Part A
Programming Languages, Part C | Core Programming | 3 weeks | 4-8 hours/week | 12 | 2021-10-11 16:48 | 2021-10-20 02:24 | 24 | 2021-11-21 07:12 | 2021-12-08 02:24 |  |  | Programming Languages, Part B
Calculus 1A: Differentiation | Math Prereq 1 Calculus | 13 weeks | 6-10 hours/week | 78 | 2021-10-20 02:24 | 2021-12-13 16:48 | 130 | 2021-12-08 02:24 | 2022-03-09 02:24 |  |  | high school math
Calculus 1B: Integration | Math Prereq 1 Calculus | 13 weeks | 5-10 hours/week | 65 | 2021-12-13 16:48 | 2022-01-28 04:48 | 130 | 2022-03-09 02:24 | 2022-06-08 02:24 |  |  | Calculus 1A
Calculus 1C: Coordinate Systems & Infinite Series | Math Prereq 1 Calculus | 6 weeks | 5-10 hours/week | 30 | 2022-01-28 04:48 | 2022-02-18 04:48 | 60 | 2022-06-08 02:24 | 2022-07-20 02:24 |  |  | Calculus 1B
Essence of Linear Algebra | Math Prereq 2 Linear Algebra | 3 weeks | 2-3 hours/week | 6 | 2021-10-20 02:24 | 2021-10-24 07:12 | 9 | 2021-12-08 02:24 | 2021-12-14 09:36 |  |  | high school math
Linear Algebra | Math Prereq 2 Linear Algebra | 13 weeks | 12 hours/week | 156 | 2021-10-24 07:12 | 2022-02-10 12:00 | 156 | 2021-12-14 09:36 | 2022-04-02 14:24 |  |  | Essence of Linear Algebra
Logic Introduction | Math Prereq 3 Logic | 10 weeks | 4-5 hours/week | 40 | 2021-10-20 02:24 | 2021-11-17 02:24 | 50 | 2021-12-08 02:24 | 2022-01-12 02:24 |  |  | set theory
Probability Introduction | Math Prereq 4 Probability | 24 weeks | 12 hours/week | 288 | 2021-10-20 02:24 | 2022-05-09 16:48 | 288 | 2021-12-08 02:24 | 2022-06-27 16:48 |  |  | Diferentiation and Integration
Mathematics for Computer Science | Core Math | 13 weeks | 5 hours/week | 65 | 2022-05-09 16:48 | 2022-06-24 04:48 | 65 | 2022-07-20 02:24 | 2022-09-03 14:24 |  |  | Calculus 1C
The Missing Semester of Your CS Education | CS Tools | 2 weeks | 12 hours/week | 24 | 2022-06-24 04:48 | 2022-07-11 | 24 | 2022-09-03 14:24 | 2022-09-20 09:36 |  |  | -
Build a Modern Computer from First Principles: From Nand to Tetris | Core Systems | 6 weeks | 7-13 hours/week | 42 | 2022-07-11 | 2022-08-09 09:36 | 78 | 2022-09-20 09:36 | 2022-11-14 |  |  | C-like programming language
Build a Modern Computer from First Principles: Nand to Tetris Part II | Core Systems | 6 weeks | 12-18 hours/week | 72 | 2022-08-09 09:36 | 2022-09-28 19:12 | 108 | 2022-11-14 | 2023-01-28 14:24 |  |  | one of these programming languages, From Nand to Tetris Part I
Operating Systems: Three Easy Pieces | Core Systems | 10-12 weeks | 6 hours/week | 60 | 2022-09-28 19:12 | 2022-11-09 19:12 | 72 | 2023-01-28 14:24 | 2023-03-20 |  |  | algorithms, familiarity with C, is useful
Introduction to Computer Networking | Core Systems | 8 weeks | 4–12 hours/week | 32 | 2022-11-09 19:12 | 2022-12-02 04:48 | 96 | 2023-03-20 | 2023-05-26 04:48 |  |  | algebra, probability, basic CS
Divide and Conquer, Sorting and Searching, and Randomized Algorithms | Core Theory | 4 weeks | 4-8 hours/week | 16 | 2022-12-02 04:48 | 2022-12-13 09:36 | 32 | 2023-05-26 04:48 | 2023-06-17 14:24 |  |  | any programming language, Mathematics for Computer Science
Graph Search, Shortest Paths, and Data Structures | Core Theory | 4 weeks | 4-8 hours/week | 16 | 2022-12-13 09:36 | 2022-12-24 14:24 | 32 | 2023-06-17 14:24 | 2023-07-10 |  |  | Divide and Conquer, Sorting and Searching, and Randomized Algorithms
Greedy Algorithms, Minimum Spanning Trees, and Dynamic Programming | Core Theory | 4 weeks | 4-8 hours/week | 16 | 2022-12-24 14:24 | 2023-01-04 19:12 | 32 | 2023-07-10 | 2023-08-01 09:36 |  |  | Graph Search, Shortest Paths, and Data Structures
Shortest Paths Revisited, NP-Complete Problems and What To Do About Them | Core Theory | 4 weeks | 4-8 hours/week | 16 | 2023-01-04 19:12 | 2023-01-16 | 32 | 2023-08-01 09:36 | 2023-08-23 19:12 |  |  | Greedy Algorithms, Minimum Spanning Trees, and Dynamic Programming
Information Security: Context and Introduction | Core Security | 5 weeks | 3 hours/week | 15 | 2023-01-16 | 2023-01-26 12:00 | 15 | 2023-08-23 19:12 | 2023-09-03 07:12 |  |  | -
Principles of Secure Coding | Core Security | 4 weeks | 4 hours/week | 16 | 2023-01-26 12:00 | 2023-02-06 16:48 | 16 | 2023-09-03 07:12 | 2023-09-14 12:00 |  |  | -
Identifying Security Vulnerabilities | Core Security | 4 weeks | 4 hours/week | 16 | 2023-02-06 16:48 | 2023-02-17 21:36 | 16 | 2023-09-14 12:00 | 2023-09-25 16:48 |  |  | -
Identifying Security Vulnerabilities in C/C++Programming | Core Security | 4 weeks | 4 hours/week | 16 | 2023-02-17 21:36 | 2023-03-01 02:24 | 16 | 2023-09-25 16:48 | 2023-10-06 21:36 |  |  | -
Exploiting and Securing Vulnerabilities in Java Applications | Core Security | 4 weeks | 5 hours/week | 20 | 2023-03-01 02:24 | 2023-03-15 02:24 | 20 | 2023-10-06 21:36 | 2023-10-20 21:36 |  |  | -
Relational Databases and SQL | Core Applications | 2 weeks | 10 hours/week | 20 | 2023-03-15 02:24 | 2023-03-29 02:24 | 20 | 2023-10-20 21:36 | 2023-11-03 21:36 |  |  | core programming
Databases: Modeling and Theory | Core Applications | 2 weeks | 10 hours/week | 20 | 2023-03-29 02:24 | 2023-04-12 02:24 | 20 | 2023-11-03 21:36 | 2023-11-17 21:36 |  |  | Relational Databases and SQL
Databases: Semistructured Data | Core Applications | 2 weeks | 10 hours/week | 20 | 2023-04-12 02:24 | 2023-04-26 02:24 | 20 | 2023-11-17 21:36 | 2023-12-01 21:36 |  |  | core programming
Machine Learning | Core Applications | 11 weeks | 4-6 hours/week | 44 | 2023-04-26 02:24 | 2023-05-26 21:36 | 66 | 2023-12-01 21:36 | 2024-01-17 02:24 |  |  | linear algebra
Computer Graphics | Core Applications | 6 weeks | 12 hours/week | 72 | 2023-05-26 21:36 | 2023-07-16 07:12 | 72 | 2024-01-17 02:24 | 2024-03-07 12:00 |  |  | C++ or Java, linear algebra
Software Engineering: Introduction | Core Applications | 6 weeks | 8-10 hours/week | 48 | 2023-07-16 07:12 | 2023-08-18 21:36 | 60 | 2024-03-07 12:00 | 2024-04-18 12:00 |  |  | Core Programming, and a sizable project
Software Development Capstone Project | Core Applications | 6-7 weeks | 8-10 hours/week | 48 | 2023-08-18 21:36 | 2023-09-21 12:00 | 70 | 2024-04-18 12:00 | 2024-06-06 12:00 |  |  | Software Engineering: Introduction
Parallel Programming | Advanced Programming | 4 weeks | 6-8 hours/week | 24 | 2023-09-21 12:00 | 2023-10-08 07:12 | 32 | 2024-06-06 12:00 | 2024-06-28 21:36 |  |  | Scala programming
Compilers | Advanced Programming | 9 weeks | 6-8 hours/week | 54 | 2023-10-08 07:12 | 2023-11-15 02:24 | 72 | 2024-06-28 21:36 | 2024-08-18 07:12 |  |  | none
Introduction to Haskell | Advanced Programming | 14 weeks | - | 100 | 2023-11-15 02:24 | 2024-01-24 02:24 | 100 | 2024-08-18 07:12 | 2024-10-27 07:12 |  |  | -
Learn Prolog Now! | Advanced Programming | 12 weeks | - | 100 | 2024-01-24 02:24 | 2024-04-03 02:24 | 100 | 2024-10-27 07:12 | 2025-01-05 07:12 |  |  | -
Software Debugging | Advanced Programming | 8 weeks | 6 hours/week | 48 | 2024-04-03 02:24 | 2024-05-06 16:48 | 48 | 2025-01-05 07:12 | 2025-02-07 21:36 |  |  | Python, object-oriented programming
Software Testing | Advanced Programming | 4 weeks | 6 hours/week | 24 | 2024-05-06 16:48 | 2024-05-23 12:00 | 24 | 2025-02-07 21:36 | 2025-02-24 16:48 |  |  | Python, programming experience
LAFF – On Programming for Correctness | Advanced Programming | 7 weeks | 4-6 hours/week | 28 | 2024-05-23 12:00 | 2024-06-12 02:24 | 42 | 2025-02-24 16:48 | 2025-03-26 02:24 |  |  | -
Software Architecture & Design | Advanced Programming | 8 weeks | 6 hours/week | 48 | 2024-06-12 02:24 | 2024-07-15 16:48 | 48 | 2025-03-26 02:24 | 2025-04-28 16:48 |  |  | software engineering in Java
Computation Structures 1: Digital Circuits | Advanced Systems | 6 weeks | 6 hours/week | 36 | 2024-07-15 16:48 | 2024-08-09 21:36 | 36 | 2025-04-28 16:48 | 2025-05-23 21:36 |  |  | Nand2Tetris
Computation Structures 2: Computer Architecture | Advanced Systems | 6 weeks | 6 hours/week | 36 | 2024-08-09 21:36 | 2024-09-04 02:24 | 36 | 2025-05-23 21:36 | 2025-06-18 02:24 |  |  | computation Structures 1
Computation Structures 3: Computer Organization | Advanced Systems | 6 weeks | 6 hours/week | 36 | 2024-09-04 02:24 | 2024-09-29 07:12 | 36 | 2025-06-18 02:24 | 2025-07-13 07:12 |  |  | computation Structures 2
Theory of Computation | Advanced Theory | 8 weeks | 10 hours/week | 80 | 2024-09-29 07:12 | 2024-11-24 07:12 | 80 | 2025-07-13 07:12 | 2025-09-07 07:12 |  |  | discrete mathematics, logic, algorithms
Computational Geometry | Advanced Theory | 16 weeks | 8 hours/week | 128 | 2024-11-24 07:12 | 2025-02-21 21:36 | 128 | 2025-09-07 07:12 | 2025-12-05 21:36 |  |  | algorithms, C++
Introduction to Formal Concept Analysis | Advanced Theory | 6 weeks | 5 hours/week | 30 | 2025-02-21 21:36 | 2025-03-14 21:36 | 30 | 2025-12-05 21:36 | 2025-12-26 21:36 |  |  | -
Game Theory | Advanced Theory | 8 weeks | 3 hours/week | 24 | 2025-03-14 21:36 | 2025-03-31 16:48 | 24 | 2025-12-26 21:36 | 2026-01-12 16:48 |  |  | matematical thinking, probability, calculus
Modern Robotics (Specialization) | Advanced Applications 1 | 26 weeks | 2-5 hours/week | 52 | 2025-03-31 16:48 | 2025-05-07 02:24 | 130 | 2026-01-12 16:48 | 2026-04-13 16:48 |  |  | freshman-level physics, linear algebra, calculus, linear ordinary differential equations
Data Mining (Specialization) | Advanced Applications 2 | 30 weeks | 2-5 hours/week | 60 | 2025-03-31 16:48 | 2025-05-12 16:48 | 150 | 2026-01-12 16:48 | 2026-04-27 16:48 |  |  | machine learning
Big Data (Specialization) | Advanced Applications 3 | 30 weeks | 3-5 hours/week | 90 | 2025-03-31 16:48 | 2025-06-02 16:48 | 150 | 2026-01-12 16:48 | 2026-04-27 16:48 |  |  | -
Internet of Things (Specialization) | Advanced Applications 4 | 30 weeks | 1-5 hours/week | 30 | 2025-03-31 16:48 | 2025-04-21 16:48 | 150 | 2026-01-12 16:48 | 2026-04-27 16:48 |  |  | strong programming
Cloud Computing (Specialization) | Advanced Applications 4 | 30 weeks | 2-6 hours/week | 60 | 2025-03-31 16:48 | 2025-05-12 16:48 | 180 | 2026-01-12 16:48 | 2026-05-18 16:48 |  |  | C++ programming
Fullstack Open (Specialization) | Advanced Applications 5 | 12 weeks | 6 hours/week | 72 | 2025-03-31 16:48 | 2025-05-21 02:24 | 72 | 2026-01-12 16:48 | 2026-03-04 02:24 |  |  | programming
Data Science (Specialization) | Advanced Applications 6 | 43 weeks | 1-6 hours/week | 43 | 2025-03-31 16:48 | 2025-04-30 19:12 | 258 | 2026-01-12 16:48 | 2026-07-12 07:12 |  |  | -
Functional Programming in Scala (Specialization) | Advanced Applications 7 | 29 weeks | 4-5 hours/week | 116 | 2025-03-31 16:48 | 2025-06-20 21:36 | 145 | 2026-01-12 16:48 | 2026-04-24 04:48 |  |  | one year programming experience
Game Design and Development (Specialization) | Advanced Applications 8 | 30 weeks | 5 hours/week | 150 | 2025-03-31 16:48 | 2025-07-14 16:48 | 150 | 2026-01-12 16:48 | 2026-04-27 16:48 |  |  | programming, interactive design
Final Project | Final Project |  |  | 100 | 2025-07-14 16:48 | 2025-09-22 16:48 | 100 | 2026-07-12 07:12 | 2026-09-20 07:12
Formulas:
Start Date = IF(ISBLANK([Actual End Date, row above]),[End Date Estimate Lower Bound, row above],[Actual End Date, row above])
Start Date = IF(ISBLANK([Actual End Date, row above]),[End Date Estimate Upper Bound, row above],[Actual End Date, row above])
End Date Estimate Lower Bound = IF(ISBLANK([Actual End Date]),[Start Date]+([Total Hours Lower Bound]/(Timeline!$B3/7)),[Actual End Date])
End Date Estimate Upper Bound = IF(ISBLANK([Actual End Date]),[Start Date]+([Total Hours Upper Bound]/(Timeline!$B3/7)),[Actual End Date])